## DAILY JOBS
s.no | Dates | Target Dates | Completion date | Address | work ID | Codes | quantity | Amount for codes | Total amount | Techs | Status | Notes
1 | 2018-02-15 | 2018-03-23 | 2018-02-19 | 34B GRASSWAYS ROAD PAKURANGA | 131078 | NGA-C12M | 3 | 46.59 | 139.77 | Kranthi-8hours | Completed
[6 empty] | NGA-C04 | 1 | 28.89 | 28.89 | babu-8 hours
[6 empty] | NGA-D01 | 12.5 | 20.8 | 260
[6 empty] | NGA-MD1A | 10.7 | 3.98 | 42.586
[6 empty] | NGA-733 | 10.7 | 5.65 | 60.455
[6 empty] | NGA-707 | 3 | 85.96 | 257.88
[6 empty] | NGA-d03 | 9.9 | 40.32 | 399.168
[6 empty] | NGA-733 | 14.6 | 5.65 | 82.49
[6 empty] | NGA-D01 | 3.1 | 20.8 | 64.48
[6 empty] | NGA-G04 | 0.93 | 21.99 | 20.4507
[6 empty] | NGA-d03 | 4.3 | 40.32 | 173.376
[6 empty] | NGA-D01 | 5.8 | 20.8 | 120.64
[6 empty] | NGA-G06 | 0.8 | 2.92 | 2.336
1652.5217
2 | 2018-02-16 | 2018-03-13 | 2018-02-20 | 27 BERT WILSON PLACE, COCKLE BAY, MANUKAU, 2014 | 132054 | NGA-C12M | 1 | 46.59 | 46.59
[6 empty] | NGA-D01 | 9.8 | 20.8 | 203.84 | kranthi-16 hours | UNDER PROGRESS | IFDB to be installed
[6 empty] | NGA-G06 | 4.8 | 2.92 | 14.016 | Lokesh- 12 hours
[6 empty] | NGA-D01 | 22 | 28.8 | 633.6 | babu-4 hours
[6 empty] | D03 | 47.4 | 40.32 | 1911.168 | Santhan - 12 hours
[6 empty] | D03 | 3.2 | 40.32 | 129.024
[6 empty] | D01 | 4 | 20.8 | 83.2
[6 empty] | D03 | 11 | 40.32 | 443.52
3464.95
3 | [5 empty] | NGA-1C14A.1 | 1 | 229.15 | 229.15
[6 empty] | MB02.1 | 1 | 40.5 | 40.5
[6 empty] | 706 | 1 | 80.46 | 80.46
[6 empty] | 758A | 1 | 59.66 | 59.66
409.77
4 | 2018-02-20 | 2018-03-23 | 2018-02-26 | 15B SAINSBURY ROAD, MOUNT ALBERT, AUCKLAND, 1025 | 132642 | NGA-C12M | 3 | 46.59 | 139.77 | Narinder- 8 hours
[6 empty] | NGA-D01 | 31.4 | 20.8 | 653.12 | Parmveer- 8 hours
[6 empty] | NGA-D01 | 12.7 | 20.8 | 264.16 | Bright- 8 hours | Completed
[6 empty] | NGA-G04 | 3.81 | 21.99 | 83.7819
[6 empty] | NGA-d03 | 5 | 40.32 | 201.6
[6 empty] | NGA-d03 | 3.9 | 40.32 | 157.248
[6 empty] | NGA-D01 | 7.3 | 20.8 | 151.84
1651.5199
5 | 2018-02-20 | 2018-03-27 | 2018-02-21 | 15 MARENDELLAS DRIVE, BUCKLANDS BEACH, MANUKAU, 2014 | 130744 | NGA-C12M | 2 | 46.59 | 93.18
[6 empty] | NGA-c04 | 2 | 28.89 | 57.78 | kranthi-5 hours | Completed
[6 empty] | NGA-d03 | 3.2 | 40.32 | 129.024 | Lokesh- 5hours
[6 empty] | NGA-d01 | 7.2 | 20.8 | 149.76 | Santhan - 5 hours
[6 empty] | NGA-733 | 44.8 | 5.65 | 253.12
[6 empty] | NGA-d03 | 4.3 | 40.32 | 173.376
856.24
6 | 2018-02-20 | 2018-03-29 | 2018-02-22 | 2/136 BRADBURY ROAD, BOTANY DOWNS, MANUKAU, 2010 | 129940 | NGA-C12M | 2 | 46.59 | 93.18
[6 empty] | NGA-D03 | 3 | 40.32 | 120.96
[6 empty] | NGA-C12M | 2 | 46.59 | 93.18 | KRANTHI- 8 hrs | Completed
[6 empty] | NGA-D01 | 45 | 20.8 | 936 | LOKESH- 8hrs
[6 empty] | NGA-D01 | 17 | 20.8 | 353.6 | Santhan - 8 hours
[6 empty] | NGA-d03 | 4.5 | 40.32 | 181.44
[6 empty] | NGA-d03 | 4 | 40.32 | 161.28
|  |  |  | NGA-D03 |  | NGA-d03 | 2 | 40.32 | 80.64
[6 empty] | NGA-D01 | 1 | 20.8 | 20.8
2041.08
7 | 2018-02-22 | 2018-03-29 | 2018-02-23 | 6A BURNSALL PLACE, AVONDALE, AUCKLAND, 1026 | 133226 | NGA-C12 M | 2 | 46.59 | 93.18 | Kranthi - 8 hours
[6 empty] | NGA-733 | 72.2 | 5.65 | 407.93 | Santhan - 8 hours
[6 empty] | D01 | 6.5 | 20.8 | 135.2 |  | Completed
[6 empty] | D03 | 3.2 | 40.32 | 129.024
[6 empty] | D03 | 4.2 | 40.32 | 169.344
[6 empty] | 733 | 10.8 | 5.65 | 61.02
995.698
8 | 2018-02-23 | 2018-03-14 |  | 44B THE DRIVE, EPSOM, AUCKLAND, 1023 | 131049 | NGA-707 | 2 | 85.96 | 171.92
[6 empty] | D01 | 45 | 20.8 | 936 |  | pending
[6 empty] | G03 | 13.5 | 128.81 | 1738.935
2846.855
9 | 2018-02-23 | 2018-03-29 | 2018-02-27 | 242C BLOCKHOUSE BAY ROAD, AVONDALE, AUCKLAND, 0600 | 133975 | NGA-B22 | 1 | 354.57 | 354.57
[6 empty] | C12M | 4 | 46.59 | 186.36
[6 empty] | D01 | 4 | 20.8 | 83.2
[6 empty] | G02 | 2 | 139.95 | 279.9 | Lokesh- 16 hours
[6 empty] | MD2 | 1 | 27.35 | 27.35 | garry- 16 hours
[6 empty] | MD1A | 17 | 3.98 | 67.66 | Shyam-6 hours | Completed
[6 empty] | 707 | 4 | 85.96 | 343.84 | Bright- 6 hours
[6 empty] | 733 | 17 | 5.65 | 96.05 | Paramveer - 6 hours
[6 empty] | D03 | 9 | 40.32 | 362.88
[6 empty] | MD1C | 30 | 8.64 | 259.2
[6 empty] | 733 | 30 | 5.65 | 169.5
[6 empty] | D03 | 4 | 40.32 | 161.28
[6 empty] | 733 | 24 | 5.65 | 135.6
[6 empty] | D03 | 9 | 40.32 | 362.88
2890.27
10 | 2018-02-23 | 2018-04-05 |  | 2/48 SACKVILLE STREET, GREY LYNN, AUCKLAND, 1021 | 132526 | NGA-707 | 2 | 85.96 | 171.92
[6 empty] | 733 | 52 | 5.65 | 293.8 | Kranthi- | under progress | OSB to be done
[6 empty] | D03 | 6 | 40.32 | 241.92 | Santhan-
[6 empty] | D03 | 3.5 | 40.32 | 141.12
[6 empty] | D03 | 13 | 40.32 | 524.16
1372.92
11 | 2018-02-23 | 2018-04-05 |  | 2/48 SACKVILLE STREET, GREY LYNN, AUCKLAND, 1021 |  | BS MISC-1 | 1
[6 empty] | BS MISC-1 | -1
12 | 2018-02-23 | 2018-04-10 | 2018-02-26 | 1D ALANBROOKE CRESCENT, AVONDALE, AUCKLAND, 0600 | 132307 | NGA-D01 | 2 | 20.8 | 41.6
[6 empty] | D03 | 6.6 | 40.32 | 266.112
[6 empty] | 733 | 54 | 5.65 | 305.1 | Kranthi- 6 hours
[6 empty] | D03 | 2.8 | 40.32 | 112.896 | Santhan-6 hours | Completed
[6 empty] | D01 | 1.9 | 20.8 | 39.52
[6 empty] | 733 | 1.7 | 5.65 | 9.605
765.228
Kranthi- 8 hours
13 | 2018-02-26 | 2018-04-06 |  | 69 MARINE PARADE, HERNE BAY, AUCKLAND, 1011 | 133054 | NGA-707 | 2 | 85.96 | 171.92 | Lokesk- 8 hours, OSB- 6 hours
[6 empty] | D03 | 31 | 40.32 | 1249.92 | Santhan-8hours OSB- 6 hours
[6 empty] | D03 | 5.8 | 40.32 | 233.856 | Garry - 6 hours | Completed
[9 empty] | 1655.696 | Narinder - OSB- 6 hours
14 | 2018-02-27 | 2018-03-29 |  | 153B RIDDELL ROAD, GLENDOWIE, AUCKLAND, 1071 | 133661 | NGA- C12M | 3 | 46.59 | 139.77
[6 empty] | 707 | 3 | 85.96 | 257.88 | Narinder- 4 hours
[6 empty] | MD1a | 42 | 3.98 | 167.16 | Bright- 4 hours
[6 empty] | 733 | 42 | 5.65 | 237.3 | Paramveer - 4 hours | under progress
[6 empty] | D03 | 12.5 | 40.32 | 504 | Kranthi - 10 hours
[6 empty] | MD1a | 30 | 3.98 | 119.4 | lokeswh - 10 hours
[6 empty] | 733 | 30 | 5.65 | 169.5 | santhan - 10 hours
[6 empty] | D03 | 5 | 40.32 | 201.6
[6 empty] | 733 | 9 | 5.65 | 50.85
1847.46
|  |  |  | 153B RIDDELL ROAD, GLENDOWIE, AUCKLAND, 1071 |  | BS MISC-1 | 1 |  |  | lokesh - 6 hours
[6 empty] | BS MISC-1 | -1 |  |  | Santhan - 6 hours
15 | 2018-02-27 | 2018-04-02 |  | 11D TARAWERA TERRACE, ST HELIERS, AUCKLAND, 1071 | 133555 | NGA-D01 | 40 | 20.8 | 832
[6 empty] | D01 | 32 | 20.8 | 665.6
[6 empty] | G06 | 27 | 2.92 | 78.84
[6 empty] | 707 | 3 | 85.96 | 257.88
[6 empty] | D03 | 3 | 40.32 | 120.96
[6 empty] | D01 | 4 | 20.8 | 83.2
[6 empty] | G06 | 4 | 2.92 | 11.68
[6 empty] | D03 | 4 | 40.32 | 161.28
[6 empty] | D01 | 10 | 20.8 | 208
[6 empty] | G06 | 10 | 2.92 | 29.2
[6 empty] | 733 | 18 | 5.65 | 101.7
[6 empty] | D01 | 2 | 20.8 | 41.6
[6 empty] | D03 | 4 | 40.32 | 161.28
[6 empty] | D01 | 5 | 20.8 | 104
[6 empty] | D01 | 6 | 20.8 | 124.8
[6 empty] | G06 | 6 | 2.92 | 17.52
[6 empty] | 733 | 15 | 5.65 | 84.75
3084.29
[6 empty] | NGA-MD1C | 6 | 8.64 | 51.84
[6 empty] | 733 | 6 | 5.65 | 33.9
[6 empty] | 707 | 1 | 85.96 | 85.96
[6 empty] | C14 | 1 | 280.87 | 280.87
[6 empty] | BMAT | 54 |  | 0
[6 empty] | 1C14A.1 | 1 | 229.15 | 229.15
[6 empty] | MB02.1 | 1 | 40.5 | 40.5
[6 empty] | 706 | 1 | 80.46 | 80.46
[6 empty] | 758B | 1 | 74.57 | 74.57
877.25
16 | 2018-03-01 | 2018-03-15 |  | 16 BROWNLEE PLACE, PUKEKOHE, PUKEKOHE, 2120 | 133655 | NGA-C12M | 2 | 46.59 | 93.18
[6 empty] | C04 | 1 | 28.89 | 28.89
[6 empty] | D01 | 149 | 20.8 | 3099.2 | Kranthi-
[6 empty] | D03 | 36 | 40.32 | 1451.52 | Lokesh | under progress
[6 empty] | G06 | 27 | 2.92 | 78.84 | Santhan
[6 empty] | G04 | 1.8 | 21.99 | 39.582
[6 empty] | 733 | 8 | 5.65 | 45.2
4836.412
|  |  |  | 16 BROWNLEE PLACE, PUKEKOHE, PUKEKOHE, 2120 (FJ) | 133655 | NGA-1C14A.1 | 2 | 229.15 | 458.3
[6 empty] | MB02.1 | 2 | 40.5 | 81
[6 empty] | 706 | 2 | 80.46 | 160.92
[6 empty] | 758B | 1 | 74.57 | 74.57
774.79
17 | 2018-03-01 | 2018-04-17 |  | 739 NEW NORTH ROAD, MOUNT ALBERT, AUCKLAND, 1025 | 133862 | NGA-C12M | 2 | 46.59 | 93.18
[6 empty] | d01 | 1 | 20.8 | 20.8
[6 empty] | d01 | 10.7 | 20.8 | 222.56
[6 empty] | d01 | 18 | 20.8 | 374.4
[6 empty] | G03 | 5.4 | 128.81 | 695.574
[6 empty] | D03 | 17.1 | 40.32 | 689.472
[6 empty] | 733 | 52.8 | 5.65 | 298.32
2394.306
18 | 2018-03-01 | 2018-04-13 |  | 8B OAKWOOD PLACE, PUKEKOHE, PUKEKOHE, 2120 | 132820 | NGA-C12M | 3 | 46.59 | 139.77
[6 empty] | C04 | 2 | 28.89 | 57.78
[6 empty] | d01 | 5.5 | 20.8 | 114.4
[6 empty] | D03 | 7.4 | 40.32 | 298.368
[6 empty] | D01 | 2 | 20.8 | 41.6
[6 empty] | D03 | 6.6 | 40.32 | 266.112
918.03
19 | 2018-03-01 | 2018-04-16 |  | 81C HELVETIA ROAD, PUKEKOHE, PUKEKOHE, 2120 | 132877 | NGA-C12M | 2 | 46.59 | 93.18
[6 empty] | 733 | 72 | 5.65 | 406.8
[6 empty] | D03 | 3 | 40.32 | 120.96
[6 empty] | 733 | 22 | 5.65 | 124.3
[6 empty] | D03 | 3 | 40.32 | 120.96
866.2
20 | 2018-03-08 | 2018-04-20 |  | 125 KERI VISTA RISE, PAPAKURA, PAPAKURA, 2110 | 133968
[6 empty] | NGA-C12M | 4 | 46.59 | 186.36
[6 empty] | D01 | 13 | 20.8 | 270.4
[6 empty] | D03 | 10.2 | 40.32 | 411.264
[6 empty] | D01 | 3.6 | 20.8 | 74.88
[6 empty] | D03 | 9 | 40.32 | 362.88
[6 empty] | D03 | 4.8 | 40.32 | 193.536
[6 empty] | D01 | 8.5 | 20.8 | 176.8
1676.12
21 | 2018-03-08 | 2018-04-18 |  | 35A KERI VISTA RISE, PAPAKURA, PAPAKURA, 2110 | 134222 | NGA-C12M | 4 | 46.59 | 186.36
[6 empty] | D01 | 27.6 | 20.8 | 574.08
[6 empty] | D03 | 2.3 | 40.32 | 92.736
[6 empty] | D03 | 2.8 | 40.32 | 112.896
[6 empty] | D03 | 2.8 | 40.32 | 112.896
[6 empty] | D01 | 1.2 | 20.8 | 24.96
[6 empty] | 733 | 32 | 5.65 | 180.8
1284.728
0

## CODES
Column1 | Column2 | Column3 | Column4 | Column5
Fibre Provisioning Codes
Code |  |  | Description | Rate
NGA-701 | Single | Provision | Code NGA-701 Scope NGA Install – Full Scope | 47.45
NGA-702 | Single | Provision | Code NGA-702 Scope NGA Install – Half Scope | 41.61
NGA-711 | Single | Provision | Code NGA-711 Provision NGA at Greenfield’s Premise | 220.38
NGA-713 | Single | Provision | Code NGA-713 Provision NGA School Connection | 131.64
NGA-714 | Single | Provision | Code NGA-714 NGA Cancellation on Arrival | 40.58
NGA-790 | Single | Provision | Code NGA-790 Installation of ONT & Network Connection | 173.43
NGA-791 | Single | Provision | Code NGA-791 Install Composite Cable | 70.38
NGA-750 | Single | Provision | Code NGA-750 Premise Networking – Site Visit | 22.37
NGA-751 | Single | Provision | Code NGA-751 – Install an additional or Relocate ONT | 143.2
NGA-752 | Single | Provision | Code NGA-752 - Install Ethernet Jack Point | 57.4
NGA-753 | Single | Provision | Code NGA-753 - Install simple CPE standard | 66.53
NGA-754 | Single | Provision | Code NGA-754 - Install complex CPE standard (Business) | 178.63
NGA-755 | Single | Provision | Code NGA-755 - Small Enclosure | 75.17
NGA-756 | Single | Provision | Code NGA-756 - Medium Enclosure | 204.02
NGA-762 | Single | Provision | Code NGA-762 - Migrate POTS to VOIP for existing NGA Connections | 59.24
Fibre Build Codes
NGA-a03 | Single | ISP Build | Code NGA-a03 - Install equipment rack | 1510.85
NGA-a04 | Single | ISP Build | Code NGA-a04 - install small router or switch into any roadside cabinet, exchange equipment rack or enclosed cabinet | 187.96
NGA-a11 | Single | Fibre | Code NGA-a11 - install optical in line attenuator drawer | 585.58
NGA-a12 | Single | Fibre | Code NGA-a12 - install mint shelf | 1300.25
NGA-a14 | Single | Fibre | Code NGA-a14 - install ofdf tie cables up to 24 fibres (single mode) | 1658.78
NGA-A16 | Single | Fibre | Code NGA-A16 – Fibre Transmission Connection Per Site – (Connectorised) | 215.29
NGA-A16A | Single | Fibre | Code NGA-A16A – Install PON Splitter | 244.37
NGA-a17 | Single | Fibre | Code NGA-a17 - fibre transmission connection (pdh, sdh, dwdm, ethernet) per site | 207.81
NGA-a17a | Single | Fibre | Code NGA-a17a - installation of optical in line attenuator | 287.1
NGA-a17c | Single | Fibre | Code NGA-a17c - fibre transmission (rq) relinquishment (pdh, sdh, dwdm, ethernet) per site | 175.88
NGA-a19 | Single | Fibre | Code NGA-a19 - fibre reservation | 0
NGA-b04 | Single | Copper Build | Code NGA-b04 - install, replace or expand a cable terminal on an existing pole | 515.66
NGA-b05 | Single | Copper Build | Code NGA-b05 - regroup a cable terminal, building terminal, rlg or distribution point | 539.08
NGA-b06 | Single | Civil berm | Code NGA-b06 - install road crossing from an RBI or UFB Network | 980.22
NGA-b07 | Single | Civil berm | Code NGA-b07 - supply and supervise installation of new ducts and bdd pits from one or more units within an industrial/commercial building to the property boundary | 366.06
NGA-b08 | Single | Civil berm | Code NGA-b08 - install new manhole and lids in roadway | 1494.2
NGA-b09 | Single | Civil berm | Code NGA-b09 - install new manhole and lids in footway or berm | 1285.62
NGA-b10 | Single | Civil berm | Code NGA-b10 - install small pit and lid less than dimensions of 1200mm | 410.37
NGA-b16 | Single | Civil berm | Code NGA-b16 - install new poles and changeover plant | 849.75
NGA-b17 | Single | Civil berm | Code NGA-b17 - dismantle terminal or building frame from network | 181.1
NGA-b18 | Single | Civil berm | Code NGA-b18 – school leadin documentation | 0
NGA-B19 | Single | Civil berm | Code NGA-B19 - Install Hand Hole | 84.48
NGA-b22 | Single | Civil berm | Code NGA-b22 - l2 traffic management (berm) | 354.57
NGA-b23 | Single | Civil berm | Code NGA-b23 - l2 traffic management (road) | 763.25
NGA-c03 | Single | Civil berm | Code NGA-c03 - install roadside equipment cabinet – passive/cross connect (any cabinet type) | 2710.64
NGA-c04 | Per meter | Civil berm | Code NGA-c04 - duct in grass | 28.89
NGA-c04a | Per meter | Civil berm | Code NGA-c04a - duct in footpath (seal) | 89.5
NGA-c04b | Per meter | Civil berm | Code NGA-c04b - duct in roadway | 103.18
NGA-c04c | Per meter | Civil berm | Code NGA-c04c - duct - thrusting | 36.1
NGA-733 | Per meter | Civil berm | Code NGA-733 Install Surface Mounted Service Conduit | 5.65
NGA-734 | Single | Civil berm | Code NGA-734 Connect Microduct and install Fibre ETP | 41.55
NGA-735 | Single | Aerial | Code NGA-735 Extend Communal Pole Infrastructure (ABF) | 131.3
NGA-736 | Single | Aerial | Code NGA-736 Extend Communal Pole Infrastructure (Aerial Fixed Fibre) | 624.09
NGA-703 | Single | Aerial | Code NGA-703 Install Aerial Lead In (1 Span) | 101.11
NGA-705 | Single | Aerial | Code NGA-705 Span Rate For Aerial Provisioning (>1 Span) | 27.13
NGA-707 | Single | Haul | Code NGA-707 Haul Fixed Fibre or Ruggedised Through Communal Network To Boundary | 85.96
NGA-741 | Single | Haul | Code NGA-741 Haul Service Lead From End of Communal Network to Fibre ETP Location | 87.16
NGA-745 | Per meter | Haul | Code NGA-745 Extra Rate for Hauling From End of Communal Network to Fibre ETP Location in Excess of 30 metres | 1.39
NGA-c12 | Per meter | Haul | Code NGA-c12 - Haul through existing empty ducts | 1.9
NGA-c12a | Per meter | Haul | Code NGA-c12a - Overhaul through ducts containing existing network | 2.48
NGA-c12b | Per meter | Haul | Code NGA-c12b - haul subduct through existing ducts | 3.28
NGA-c12c | Per meter | Haul | Code NGA-c12c - haul extra subduct through existing ducts | 2.96
NGA-c12d | Single | Haul | Code NGA-c12d – fibre loops in manholes | 122.1
NGA-706 | Single | Blow | Code NGA-706 Blow fibre through 5mm tube From FFP or ABFAT to Fibre ETP | 80.46
NGA-c12g | Per meter | Blow | Code NGA-c12g – blow air blown fibre cable through Microducts | 1.4
NGA-c12ga | Per meter | Blow | Code NGA-c12ga – blow air blown fibre cable through Microducts | 1.32
NGA-c12h | Single | Blow | Code NGA-c12h – air blown fibre loops in manholes | 173.72
NGA-C12M | Single | Civil berm | Code NGA-C12M – Joint single-Way Microduct | 46.59
NGA-c12i | Single | Civil berm | Code NGA-c12i – joint 2-4 way Microduct | 47.12
NGA-c12j | Single | Civil berm | Code NGA-c12j – joint 5-7 way Microduct | 51.6
NGA-C12L | Single | Civil berm | Code NGA-C12L – Joint 8-12 Way Microduct | 56.07
NGA-c12k | Single | Civil berm | Code NGA-c12k – joint 13-26 way Microduct | 65.02
NGA-c14 | Single | Fibre | Code NGA-c14 - joint fibre cables (1-12 splices) | 280.87
NGA-c14.1 | Single | Fibre | Code NGA-c14.1 - joint fibre cables (13-24 splices) | 480.96
NGA-c14.2 | Single | Fibre | Code NGA-c14.2 - joint fibre cables (25-48 splices) | 783.93
NGA-c14.3 | Single | Fibre | Code NGA-c14.3 - joint fibre cables (49-96 splices) | 1238.28
NGA-c14.4 | Single | Fibre | Code NGA-c14.4 - joint fibre cables (97-144 splices) | 1798.07
NGA-c14.5 | Single | Fibre | Code NGA-c14.5 - joint fibre cables (145-216 splices) | 2460.35
NGA-c14.6 | Single | Fibre | Code NGA-c14.6 - joint fibre cables (217-312 splices) | 3116.67
NGA-c14a | Single | Fibre | Code NGA-c14a - install a fibre closure | 148.34
NGA-RO1 | Single | Civil Inside | Code NGA-RO1 – Inside Boundary Mobilisation (Civils) | 0
NGA-D01 | Per meter | Civil Inside | Code NGA-D01 - Inside Boundary Trenching - Base Rate | 20.8
NGA-D02 | Per meter | Civil Inside | Code NGA-D02 - Inside Boundary Trenching - Slot Trenching – Soft Surface | 20.8
NGA-D03 | Per meter | Civil Inside | Code NGA-D03 - Inside Boundary Trenching - Slot Trenching – Hard Surface | 40.32
NGA-E01 | Per meter | Civil Inside | Code NGA-E01 – Inside Boundary Drilling & Thrusting – Base Rate | 35.8
NGA-G01 | Per Sq meter | Civil Inside | Code NGA-G01 – Inside Boundary Reinstatement - Seal & Chip Seal | 75.88
NGA-G02 | Per Sq meter | Civil Inside | Code NGA-G02 – Inside Boundary Reinstatement - Concrete | 139.95
NGA-G03 | Per Sq meter | Civil Inside | Code NGA-G03 – Inside Boundary Reinstatement - Concrete Aggregate | 128.81
NGA-G04 | Per meter | Civil Inside | Code NGA-G04 – Inside Boundary Reinstatement - Gravel | 21.99
NGA-G05 | Per meter | Civil Inside | Code NGA-G05 – Inside Boundary Reinstatement - Rock | 31.44
NGA-G06 | Per meter | Civil Inside | Code NGA-G06 – Inside Boundary Reinstatement Gardens & Decorative Areas | 2.92
NGA-MC21 | Single | Civil Inside | Code NGA-MC21 Inside Boundary Locate, Dig & Repair Blocked or Damaged Duct | 113.84
NGA-757 | Single | Design | Code NGA-757 Network/Cable route plan - Non MDU | 0
NGA-757a | Single | Design | Code NGA-757a Network/Cable route plan - Class 1 MDU/ROW 2-5 | 0
NGA-757b | Single | Design | Code NGA-757b Network/Cable route plan - Class 2 MDU/ROW 6-12 | 0
NGA-757c | Single | Design | Code NGA-757d Network/Cable route plan - Class 3 MDU/ROW 13-48 | 0
NGA-757d | Single | Design | Code NGA-757e Network/Cable route plan - Class 4 MDU/ROW 49+ | 0
NGA-758 | Single | MDU | Code NGA-758 Mobilisation - Non MDU | 33.56
NGA-758a | Single | MDU | Code NGA-758a Mobilisation - Class 1 MDU/ROW 2-5 | 59.66
NGA-758b | Single | MDU | Code NGA-758b Mobilisation - Class 2 MDU/ROW 6-12 | 74.57
NGA-758c | Single | MDU | Code NGA-758c Mobilisation - Class 3 MDU/ROW 13-48 | 261.74
NGA-758d | Single | MDU | Code NGA-758d Mobilisation - Class 4 MDU/ROW 49+ | 575.37
NGA-759 | Single | Design | Code NGA-759 Records & Completion - Non MDU | 0
NGA-759a | Single | Design | Code NGA-759a Records & Completion - Class 1 MDU/ROW 2-5 | 0
NGA-759b | Single | Design | Code NGA-759b Records & Completion - Class 2 MDU/ROW 6-12 | 0
NGA-759c | Single | Design | Code NGA-759c Records & Completion - Class 3 MDU/ROW 13-48 | 0
NGA-759d | Single | Design | Code NGA-759d Records & Completion- Class 4 MDU/ROW 49+ | 0
NGA-Ia14a | Single | MDU | Code NGA-Ia14a – Install Building Cabling and/or Microduct | 8.58
NGA-Ia14b.1 | Single | MDU | Code NGA-Ia14b.1 – Install Support System for Cable And/Or Microduct Standard Capping | 11.39
NGA-Ia14b.2 | Single | MDU | Code NGA-Ia14b.2 – Install Support System for Cable And/Or Microduct Architrave Capping | 16.83
NGA-Ia14b.3 | Single | MDU | Code NGA-Ia14b.3 – Install Support System for Cable And/Or Microduct Catenary wire | 9.93
NGA-Ia14b.4 | Single | MDU | Code NGA-Ia14b.4 – Install Support System for Cable And/Or Microduct Cable Tray | 71.8
NGA-Ia14b.5 | Single | MDU | Code NGA-Ia14b.5 – Install Support System for Cable And/Or Microduct uPVC conduit | 8.59
NGA-Ic14a.1 | Single | Fibre | Code NGA-Ic14a.1 – Install Fibre Access Terminal Budi | 229.15
NGA-Ic14a.2 | Single | Fibre | Code NGA-Ic14a.2 – Install Fibre Access Terminal GPX | 495.34
NGA-760 | Single | Civil berm | Code NGA-760 – Standard Lateral | 288.03
NGA-761 | Single | Civil berm | Code NGA-761 – Standard Lateral Extra Rate for additional tubes | 13.61
Consumables by Set Variation
NGA-MA03 | Single | Material | Code NGA-MA03 - DC power supply for A03 MAR inclusive of a minimum ten MCB’s. “ Provide FUSE PANEL 20 circuit 19” where required | 1935.62
NGA-MA14 | Single | Material | Code NGA-MA14 - 24 fibre cable tie | 79.66
NGA-MB07 | Single | Material | Code NGA-MB07 - 6 metre duct length | 33.68
NGA-MB08.1 | Single | Material | Code NGA-MB08.1 - Aluminium Manhole and lid 1.2x0.6x0.7 | 2709.97
NGA-MB08.2 | Single | Material | Code NGA-MB08.2 - Aluminium Manhole and lid 1.2x1.2x0.7 | 4826.31
NGA-MB08.3 | Single | Material | Code NGA-MB08.3 - Aluminium Manhole and lid 2.1x1.2x0.7 | 5726.16
NGA-MB08.4 | Single | Material | Code NGA-MB08.4 - Aluminium Manhole and lid 2.1x1.2x1.2 | 5159.86
NGA-MB08.5 | Single | Material | Code NGA-MB08.5 - Concrete Manhole with lids 1.2x0.6x0.6 | 2474.74
NGA-MB08.6 | Single | Material | Code NGA-MB08.6 - Concrete Manhole with lids 1.2x0.6x0.9 | 2794.83
NGA-MB08.7 | Single | Material | Code NGA-MB08.7 - Concrete Manhole with lids 1.2x1.2x0.9 | 4920.99
NGA-MB08.8 | Single | Material | Code NGA-MB08.8 - Concrete Manhole with lids 2.1x1.2x1.2 | 6223.94
NGA-MB08.9 | Single | Material | Code NGA-MB08.9 - Additional rate for rock(for manholes only) | 363.83
NGA-MB09.1 | Single | Material | Code NGA-MB09.1 - Aluminium Manhole and lid 1.2x0.6x0.7 | 1790.12
NGA-MB09.2 | Single | Material | Code NGA-MB09.2 - Aluminium Manhole and lid 1.2x1.2x0.7 | 3176.46
NGA-MB09.3 | Single | Material | Code NGA-MB09.3 - Aluminium Manhole and lid 2.1x1.2x0.7 | 4726.7
NGA-MB09.4 | Single | Material | Code NGA-MB09.4 - Aluminium Manhole and lid 2.1x0.6x0.7 | 3324.96
NGA-MB09.5 | Single | Material | Code NGA-MB09.5 - Concrete Manhole with lids 1.2x0.6x0.6 | 1449.42
NGA-MB09.6 | Single | Material | Code NGA-MB09.6 - Concrete Manhole with lids 1.2x1.2x0.9 | 2995.69
NGA-MB09.7 | Single | Material | Code NGA-MB09.7 - Concrete Manhole with lids 2.1x1.2x0.8 | 3648.76
NGA-MB09.8 | Single | Material | Code NGA-MB09.8 - Concrete Manhole with lids 2.1x1.2x1.2 | 4736.82
NGA-MB09.9 | Single | Material | Code NGA-MB09.9 - Plastic pit and lid | 199.93
NGA-MB10.1 | Single | Material | Code NGA-MB10.1 - Concrete pit and lid 0.6 x 0.6 x 0.6 | 979.06
NGA-MB10.2 | Single | Material | Code NGA-MB10.2 - Aluminium pit and lid 0.6x 0.7x 0.6 | 1633.21
NGA-MB10.3 | Single | Material | Code NGA-Code NGA-MB10.3 - Channell Pit SGLB1730 | 445.5
NGA-MB10.4 | Single | Material | Code NGA-Code NGA-MB10.4 - Channell Pit SGLB2436 | 597.96
NGA-MB10.5 | Single | Material | Code NGA-Code NGA-MB10.5 - Channell Pit SGLB2448 | 1238.49
NGA-MB10.6 | Single | Material | Code NGA-Code NGA-MB10.6 - Channell Pit SGLB3048 | 1635.48
NGA-MB19.1 | Single | Material | Code NGA-Code NGA-MB19.1 - Hand Hold GLB912-T | 41.58
NGA-MB19.2 | Single | Material | Code NGA-Code NGA-MB19.2 - Hand Hold GLB912C | 23.27
NGA-MC2 | Single | Material | Code NGA-MC2 - 144 Fibre Verticasa Riser cable, including any bends & riser break-outs and other consumables | 16.54
NGA-MP1 | Single | Material | Code NGA-MP1 - Connectorised fibre patchcord (all connector types) | 41.99
NGA-MP3 | Single | Material | Code NGA-MP3 - Supply of “Pass” FIP trace to Chorus | 13.73
NGA-MC04.1 | Single | Civil berm | Code NGA-MC04.1 - Additional rate for rock | 49.07
NGA-MC04.2 | Single | Civil berm | Code NGA-MC04.2 - Supply and install additional duct | 6.41
NGA-MC04A.1 | Single | Civil berm | Code NGA-MC04A.1 - Extra rate for concrete (Footpath) | 39.95
NGA-MC04B.1 | Single | Civil berm | Code NGA-MC04B.1 - Extra rate for concrete (Roadway) | 83.6
NGA-MC04C.1 | Single | Civil berm | Code NGA-MC04C.1 - Additional duct | 6.43
NGA-MC12 | Single | Civil berm | Code NGA-MC12 - Repair blocked or damaged duct | 263.35
NGA-MC12A | Single | Civil berm | Code NGA-MC12A - Repair blocked or damaged duct | 263.35
NGA-MC12B | Single | Civil berm | Code NGA-MC12B - Repair blocked or damaged duct | 263.35
NGA-MC12C | Single | Civil berm | Code NGA-MC12C - Repair blocked or damaged duct | 263.35
NGA-MC14.1 | Single | Material | Code NGA-MC14.1 - OFDF drawers containing SFOs | 1140.81
NGA-MC14A.1 | Single | Material | Code NGA-MC14A.1 - Large Fibre closure (Fist BD or BE) | 721.62
NGA-MC14A.2 | Single | Material | Code NGA-MC14A.2 - Medium Fibre closure (Fist BC) | 607.13
NGA-MC14A.3 | Single | Material | Code NGA-MC14A.3 - Small Fibre closure (Fist FD) | 128.63
NGA-MC14A.4 | Single | Material | Code NGA-MC14A.4 - Fosc closure 400/B (A) check | 1000.18
NGA-MC14A.5 | Single | Material | Code NGA-MC14A.5 - Fosc closure 400/C (B) check | 491.2
NGA-MC14A.6 | Single | Material | Code NGA-MC14A.6 - Fosc closure 400/D | 646.38
NGA-MC14.7 | Single | Material | Code NGA-MC14.7 - 24 fibre “D” series from cable well to MFODF and into fibrenet draw and SFOs (no splicing) | 10.75
NGA-MD1 | Single | Material | Code NGA-MD1 - green 20mm pipe – glued (below ground) including any bends, glue & other consumables | 9.39
NGA-MD1a | Single | Material | Code NGA-MD1a - 20mm HDPE pipe (surface mounted) including any bends & glue, but excluding saddles & screws | 3.98
NGA-MD1b | Single | Material | Code NGA-MD1b - Marley 32mm uPVC 4m pipe (surface mounted) including any bends & glue, but excluding saddles & screws | 8.64
NGA-MD1c | Single | Material | Code NGA-MD1c - Grey 32mm HDPE 5m pipe (surface mounted) including any bends & glue, but excluding saddles & screws | 8.64
NGA-MD2 | Single | Material | Code NGA-MD2 - 50mm duct – rubber ring join including any bends & other consumables | 27.35
NGA-MD4 | Single | Material | Code NGA-MD4 - green 32mm continuous duct (below ground) including any bends & other consumables | 1.75
NGA-MD5 | Single | Material | Code NGA-MD5 - 63mm continuous duct including any bends & other consumables | 5.07
NGA-MC04.3 | Single | Material | Code NGA-MC04.3 - Additional Duct (labour only, consigned duct) | 11.64
NGA-MC04c.2 | Single | Material | Code NGA-MC04c.2 - Additional Duct (labour only, consigned duct e.g. Microduct) | 1.94
NGA-MB02.1 | Single | Material | Code NGA-MB02.1 - Pedestal | 40.5
NGA-MT1 | Single | Material | Code NGA-MT1 - T-Dux 50mm | 38.58
NGA-MT2 | Single | Material | Code NGA-MT2 - T-dux 100mm | 41.83
SDU All encomposing codes
ZNGA560A | Single | Provision | NGA Aerial SDU Installation - Scope VPL Managed Job | 3.86
ZNGA560B | Single | Provision | NGA Aerial SDU Installation - Build VPL Managed Job | 187.32
ZNGA560C | Single | Provision | NGA Aerial SDU Installation - Connect VPL Managed Job | 196.03
ZNGA560BC | Single | Provision | NGA Aerial SDU Installation - Build, Connect Contractor manged job | 414.92
ZNGA561A | Single | Provision | NGA Haull SDU Installation - Scope VPL Managed Job | 36.69
ZNGA561B | Single | Provision | NGA Haull SDU Installation - Build VPL Managed Job | 194.94
ZNGA561C | Single | Provision | NGA Haull SDU Installation - Connect VPL Managed Job | 205.64
ZNGA561BC | Single | Provision | NGA Haull SDU Installation - Build, Connect Contractor manged job | 433.57
ZNGA562A | Single | Provision | NGASurface Mount SDU Installation - Scope VPL Managed Job | 36.69
ZNGA562B | Single | Provision | NGASurface Mount SDU Installation - Build VPL Managed Job | 254.64
ZNGA562C | Single | Provision | NGASurface Mount SDU Installation - Connect VPL Managed Job | 205.64
ZNGA562BC | Single | Provision | NGASurface Mount SDU Installation - Build, Connect Contractor manged job | 498.69
ZNGA563A | Single | Provision | NGAGrass trench SDU Installation - Scope VPL Managed Job | 36.69
ZNGA563B | Single | Provision | NGAGrass trench SDU Installation - Build VPL Managed Job | 383.5
ZNGA563C | Single | Provision | NGAGrass trench SDU Installation - Connect VPL Managed Job | 205.64
ZNGA563BC | Single | Provision | NGAGrass trench SDU Installation - Build, Connect Contractor manged job | 626.7
ZNGA564A | Single | Provision | NGA Drill SDU Installation - Scope VPL Managed Job | 36.69
ZNGA564B | Single | Provision | NGA Drill SDU Installation - Build VPL Managed Job | 625.48
ZNGA564C | Single | Provision | NGA Drill SDU Installation - Connect VPL Managed Job | 205.64
ZNGA564BC | Single | Provision | NGA Drill SDU Installation - Build, Connect Contractor manged job | 881.69
ZNGA565A | Single | Provision | NGA Concrete trench SDU Installation - Scope VPL Managed Job | 36.69
ZNGA565B | Single | Provision | NGA Concrete trench SDU Installation - Build VPL Managed Job | 763.48
ZNGA565C | Single | Provision | NGA Concrete trench SDU Installation - Connect VPL Managed Job | 205.64
ZNGA565BC | Single | Provision | NGA Concrete trench SDU Installation - Build, Connect Contractor manged job | 1027.11

## Sheet1 (hidden)
19 | 2018-03-01 | 2018-04-16 | 81C HELVETIA ROAD, PUKEKOHE, PUKEKOHE, 2120 | 132877 | NGA-C12M | 2 | 46.59 | 93.18
[5 empty] | 733 | 72 | 5.65 | 406.8
[5 empty] | D03 | 3 | 40.32 | 120.96
[5 empty] | 733 | 22 | 5.65 | 124.3
[5 empty] | D03 | 3 | 40.32 | 120.96
866.2