## Project Tracker
Project Tracker
| Percent Over/Under to Flag: | 25%
Project | Category | Assigned To | Estimated Start | Estimated Finish | Estimated Work (in hours) | Estimated Duration (in days) | Actual Start | Actual Finish | Flag icon for Over/Under Actual Work (in hours) | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | Actual Duration (in days) | Notes
Project 1 | Category 1 | Employee 1 | 2018-01-15 | 2018-03-16 | 210 | 61 | 2018-01-15 | 2018-03-21 | 1 | 300 | 0 | 66
Project 2 | Category 2 | Employee 4 | 2018-02-08 | 2018-03-11 | 400 | 33 | 2018-02-08 | 2018-03-14 | 0 | 390 | 0 | 36
Project 3 | Category 1 | Employee 2 | 2017-12-11 | 2018-02-09 | 500 | 58 | 2017-12-11 | 2018-02-22 | 0 | 500 | 0 | 71
Project 4 | Category 2 | Employee 3 | 2017-12-21 | 2017-12-31 | 250 | 10 | 2017-12-21 | 2018-01-09 | 0 | 276 | 1 | 18
Project 5 | Category 3 | Employee 2 | 2017-12-21 | 2018-01-30 | 300 | 39 | 2017-12-21 | 2018-02-05 | 0 | 310 | 0 | 44
Project 6 | Category 4 | Employee 4 | 2018-01-20 | 2018-01-30 | 500 | 10 | 2018-01-20 | 2018-02-04 | 0 | 510 | 1 | 14
Project 7 | Category 5 | Employee 1 | 2018-02-05 | 2018-03-01 | 750 | 26 | 2018-02-05 | 2018-03-06 | 0 | 790 | 0 | 31
Project 8 | Category 2 | Employee 1 | 2018-02-10 | 2018-03-21 | 450 | 41 | 2018-02-04 | 2018-03-16 | 0 | 430 | 0 | 42
project 9 | Category 4 | Employee 1 | 2016-02-05 | 2016-06-09 | 250 | 124 | 2016-03-05 | 2016-05-05 | 0 | 200 | 1 | 60
SETUP

## Setup
Setup
Category Name | Employee Name
Category 1 | Kranthi
Category 2 | Santhan
Category 3 | Lokesh
Category 4 | Garry
Category 5
Category 6
PROJECTS

## FM list
Areas Covered | Field Manager | Phone Number | Email Address
HCK-NP07 | Greg Tuanau | 027 205 1919 | Gregory.Tuanau@visionstream.co.nz
PGA-NP07 | Greg Tuanau | 027 205 1919 | Gregory.Tuanau@visionstream.co.nz
MNR-NP07 | Neil Panther | 027 839 2400 | Neil.Panther@visionstream.co.nz
PAK-NP07 | Neil Panther | 027 839 2400 | Neil.Panther@visionstream.co.nz
PUK-NP07 | Neil Panther | 027 839 2400 | Neil.Panther@visionstream.co.nz
WH-NP07 | Neil Panther | 027 839 2400 | Neil.Panther@visionstream.co.nz
WKU-NP07 | Neil Panther | 027 839 2400 | Neil.Panther@visionstream.co.nz
ETM-NP07 | Regan Foai | 027 704 6965 | Regan.Foai@visionstream.co.nz
MKY-NP07 | Regan Foai | 027 704 6965 | Regan.Foai@visionstream.co.nz
MRE-NP07 | Regan Foai | 27 704 6965 | Regan.Foai@visionstream.co.nz
OAA-NP07 | Regan Foai | 27 704 6965 | Regan.Foai@visionstream.co.nz
OH-NP07 | Regan Foai | 27 704 6965 | Regan.Foai@visionstream.co.nz
POP-NP07 | Regan Foai | 27 704 6965 | Regan.Foai@visionstream.co.nz
MAB-NP08 | Regan Foai | 27 704 6965 | Regan.Foai@visionstream.co.nz
MOD-NP08 | Regan Foai | 27 704 6965 | Regan.Foai@visionstream.co.nz
MTL-NP08 | Regan Foai | 27 704 6965 | Regan.Foai@visionstream.co.nz
ON-NP08 | Regan Foai | 27 704 6965 | Regan.Foai@visionstream.co.nz
TIS-NP08 | Regan Foai | 27 704 6965 | Regan.Foai@visionstream.co.nz
TMK-NP08 | Regan Foai | 27 704 6965 | Regan.Foai@visionstream.co.nz
BD-NP09 | Graeme Bell | 027 482 7348 | graeme.bell@visionstream.co.nz
BKL-NP09 | Graeme Bell | 027 482 7348 | graeme.bell@visionstream.co.nz
GLF-NP09 | Graeme Bell | 027 482 7348 | graeme.bell@visionstream.co.nz
MSY-NP09 | Graeme Bell | 027 482 7348 | graeme.bell@visionstream.co.nz
ALY-NP09 | Glenn Harrison | 027 596 9134 | Glenn.Harrison@visionstream.co.nz
BSY-NP09 | Glenn Harrison | 027 596 9134 | Glenn.Harrison@visionstream.co.nz
DA-NP09 | Glenn Harrison | 027 596 9134 | Glenn.Harrison@visionstream.co.nz
FOR-NP09 | Glenn Harrison | 027 596 9134 | Glenn.Harrison@visionstream.co.nz
GNH-NP09 | Glenn Harrison | 027 596 9134 | Glenn.Harrison@visionstream.co.nz
TBY-NP09 | Glenn Harrison | 27 596 9134 | Glenn.Harrison@visionstream.co.nz
TNA-NP09 | Glenn Harrison | 27 596 9134 | Glenn.Harrison@visionstream.co.nz
HBC-NP10 | Glenn Harrison | 27 596 9134 | Glenn.Harrison@visionstream.co.nz
RDB-NP10 | Glenn Harrison | 27 596 9134 | Glenn.Harrison@visionstream.co.nz
AT-NP08 | Andrew McKinnon | 027 262 8318 | Andrew.Mckinnon@visionstream.co.nz
ELL-NP08 | Andrew McKinnon | 027 262 8318 | Andrew.Mckinnon@visionstream.co.nz
GDW-NP08 | Andrew McKinnon | 027 262 8318 | Andrew.Mckinnon@visionstream.co.nz
POY-NP08 | Andrew McKinnon | 027 262 8318 | Andrew.Mckinnon@visionstream.co.nz
RUE-NP08 | Andrew McKinnon | 027 262 8318 | Andrew.Mckinnon@visionstream.co.nz
SHB-NP08 | Andrew McKinnon | 027 262 8318 | Andrew.Mckinnon@visionstream.co.nz
AVD-NP08 | Davlyn Brider | 027 614 1974 | Davlyn.Brider@visionstream.co.nz
NLN-NP08 | Davlyn Brider | 027 614 1974 | Davlyn.Brider@visionstream.co.nz
GLE-NP09 | Davlyn Brider | 027 614 1974 | Davlyn.Brider@visionstream.co.nz
HSN-NP09 | Davlyn Brider | 027 614 1974 | Davlyn.Brider@visionstream.co.nz
KME-NP09 | Davlyn Brider | 027 614 1974 | Davlyn.Brider@visionstream.co.nz
TAT-NP09 | Davlyn Brider | 027 614 1974 | Davlyn.Brider@visionstream.co.nz
TGN-NP09 | Davlyn Brider | 027 614 1974 | Davlyn.Brider@visionstream.co.nz
WEI-NP09 | Davlyn Brider | 027 614 1974 | Davlyn.Brider@visionstream.co.nz

## Row Build Project
Project Tracker
Percent Over/Under to Flag:
Patch/Area | Work ID | Project Name | Assigned To | Payment | Job Status | Target Date | Estimated Work (in hours) | Estimated Duration (in days) | Actual Finish | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | Actual Duration (in days) | Field Manager | FM Email ID | Comments
| 133655 | PUK: A: Brownlee PL - AKL - 16(NGA-ROW) - Vodafone (133655) |  | 5611 | Completed | 2018-03-15 |  |  | 2018-03-15 |  |  |  |  | #N/A
| 131078 | PGA: A: Grassways AVE - AKL - 34, Unit B (NGA-ROW) - Telecom Retail (131078) |  | 1652 | Completed | 2018-03-23 |  |  | 2018-02-19 |  |  |  |  | #N/A
HCK-NP07 | 132054 | HCK: Bert Wilson PL - AKL - 27A(NGA-ROW) - CallPlus (132054) |  | 5527 | Started | 2018-03-26 | [6 empty] | Greg Tuanau | Gregory.Tuanau@visionstream.co.nz | IFDB to be installed
| 130744 | HCK: A: Marendellas DR - AKL - 15 (NGA-ROW) - Telecom Retail (130744) |  | 856 | Completed | 2018-03-27 |  |  | 2018-02-21 |  |  |  |  | Gregory.Tuanau@visionstream.co.nz
HCK-NP07 | 129940 | HCK: A: Bradbury RD - AKL - 134, Unit 1 (NGA-ROW) - Telecom Retail (129940) |  | 2041 | Completed | 2018-03-29 |  |  | 2018-02-22 |  |  |  | Greg Tuanau | #N/A
AVD-NP08 | 133975 | AVD: A: Blockhouse Bay RD - AKL - 242, Unit C(NGA-ROW) - Telecom Retail (133975) |  | 2890 | Completed | 2018-03-29 |  |  | 2018-02-27 |  |  |  | Davlyn Brider | Gregory.Tuanau@visionstream.co.nz
GDW-NP08 | 133661 | GDW: A: Riddell RD - AKL - 153B(NGA-ROW) - Telecom Retail (133661) |  | 1847 | Completed | 2018-03-29 |  |  | 2018-03-06 |  |  |  | Andrew McKinnon | Davlyn.Brider@visionstream.co.nz
GDW-NP08 | 133555 | GDW: A: Tarawera TCE - AKL - 11D(NGA-ROW) - Vodafone (133555) |  | 3961 | Started | 2018-04-02 | [6 empty] | Andrew McKinnon | Andrew.Mckinnon@visionstream.co.nz
POY-NP08 | 132526 | POY: A: Sackville ST - AKL - 48, Unit 2(NGA-ROW) - Vodafone (132526) |  | 1372 | Started | 2018-04-05 | [6 empty] | Andrew McKinnon | Andrew.Mckinnon@visionstream.co.nz | OSB TO BE DONE
POY-NP08 | 133054 | POY: A: Marine Parade - AKL - 69(NGA-ROW) - Telecom Retail (133054) |  | 1655 | Completed | 2018-04-06 |  |  | 2018-03-03 |  |  |  | Andrew McKinnon | Andrew.Mckinnon@visionstream.co.nz
HCK-NP07 | 127520 | HCK: A: Renlee PL - AKL - 17(NGA-ROW) - CallPlus (127520) |  | 5968 | To be started | 2018-04-06 | [6 empty] | Greg Tuanau | Andrew.Mckinnon@visionstream.co.nz
OH-NP07 | 133174 | OH: Panama RD - WLG - 392(NGA-ROW) - CallPlus (133174) |  | 1880 | To be started | 2018-04-09 | [6 empty] | Regan Foai | Gregory.Tuanau@visionstream.co.nz
PUK-NP07 | 132820 | PUK: A: Oakwood PL - AKL - 8B(NGA-ROW) - Vodafone (132820) |  | 918 | Completed | 2018-04-13 |  |  | 2018-03-14 |  |  |  | Neil Panther | Regan.Foai@visionstream.co.nz
PUK-NP07 | 132877 | PUK: A: Helvetia RD - AKL - 81C(NGA-ROW) - Telecom Retail (132877) |  | 866 | Completed | 2018-04-16 |  |  | 2018-03-13 |  |  |  | Neil Panther | Neil.Panther@visionstream.co.nz
MAB-NP08 | 133862 | MAB: A: New North RD - AKL - 739(NGA-ROW) - CallPlus (133862) |  | 2394 | To be started | 2018-04-17 | [6 empty] | Regan Foai | Neil.Panther@visionstream.co.nz | Modification in plan
PAK-NP07 | 134222 | PAK: A: Keri Vista RISE - AKL - 35A(NGA-ROW) - Vodafone (134222) |  | 1284 | Completed | 2018-04-18 |  |  | 2018-03-19 |  |  |  | Neil Panther | Regan.Foai@visionstream.co.nz
PAK-NP07 | 133968 | PAK: A: Keri Vista RISE - AKL - 125(NGA-ROW) - Snap (133968) |  | 1676 | Completed | 2018-04-20 |  |  | 2018-03-16 |  |  |  | Neil Panther | Neil.Panther@visionstream.co.nz
SETUP